## Resources
Project Parameters |  |  |  | Control Panel
[9 empty] | Days | Holiday Dates | 2
Project Name |  | New Project |  | Pre-Define Input Parameters: |  |  |  |  | Weeks | Email Texts
Project Manager |  | Manager's Name |  | Email Texts |  |  |  |  | Months | Project Phases: | 0
PREPARATION
Project Start Date |  | 2003-05-01 | [7 empty] | PROJECT DEFINITION
Status Report Date |  | 2026-07-30 22:21 | [7 empty] | ANALYSIS
Project Deadline |  | 2003-05-16 | [7 empty] | DESIGN
DEVELOPMENT
Scheduling Frequency |  | Days | [7 empty] | TESTING
IMPLEMENTATION
ACCEPTANCE
REVIEW
Human Resources |  |  |  | Financial Resources | [5 empty] | CLOSE-DOWN
OPERATIONAL SUPPORT
Working Hours per day | 8 |  |  | Input Denomination | $0 |  | Capital Expenditure | 0
Project Participants: |  |  |  | Budgeted Operating Costs:
Name | Cost/Hr | Email Address | Factor | Unit Type | Units | Avg Cost | Budget | Contingency
|  |  |  | Hours | 0 | 0 | 0 | 0
Total Available Productivity |  |  | 0%
|  |  |  | Total Budgeted Costs |  |  | 0 | 0
Manage Project Task List
Create Scheduling Chart
Run Project Status Report
Create Workbooks & Email
Update from External Files

## Tasks
Task Description |  |  | Dependencies & Deliverables |  | Operating Costs |  |  |  | Capital | Staffing |  |  | Timing (Dates) |  | Progress |  | Completion | Opex/ | Operating | Capex |  | Start | Schedule
ID | Phase | Description | DepID | Deliverables | Type | Cost | Units | Total | Costs | Person | Hours | Productivity | Start | End | Units | Capex | Date | Hour | Budgeted | Budgeted | Contingency | Specified | Data
0
| Totals | [6 empty] | 0 | 0 |  | 0 | 0%

## Schedule
Day Beginning:
TASKS
FULL-TIME HOURS
Scheduled
Completed
COSTS (as at Task end)
Operating Costs
Capital Costs
Total Costs

## Status
New Project project status report as at
(Start date: , Earned Value analysis denomination: $0)
| Earned Value Analysis | Performance Measurements |  |  | Variances |  | Indices
| Unit Type | BCWS | BCWP | ACWP | Cost | Schedule | CPI | SPI
| Total Operating Costs | 0 | 0 | 0 | 0 | 0 | 0% | 0%
| Capital Expenditure | 0 | 0 | 0 | 0 | 0 | 0% | 0%
| Total Project Costs | 0 | 0 | 0 | 0 | 0 | 0% | 0%
| Cost Risk Analysis | Operating | Capex | Total |  | Project Timing
| Budgeted Project Costs | 0 | 0 | 0 |  | Projected Duration
| (with Contingency) | 0 | 0 | 0 |  | Project Deadline
| Projected Project Costs | 0 | 0 | 0 |  | Predicted End Date
| Recovery Costs | 0 | 0 | 0 |  | Overrun/(Under run)
| Completion Analysis | Number of Units |  |  | Remaining Units |  | Percent Complete
| Unit Type | Budgeted | Scheduled | Completed | Budget | Schedule | Budget | Schedule
| Totals | 0 | 0 | 0 | 0 | 0
| Snapshot History | Performance Indicies
| Status Report Date | CPI | SPI
| 2003-05-01 | 0% | 0%
Note on D8: Budgeted Cost of Work Scheduled
Note on D31: Cost Performance Index
Note on E8: Budgeted Cost of Work Performed
Note on E31: Schedule Performance Index
Note on F8: Actual Cost of Work Performed
Note on I8: Cost Performance Index
Note on J8: Schedule Performance Index

## Pre-Defined
PREPARATION | PROJECT DEFINITION | ANALYSIS | DESIGN | DEVELOPMENT | TESTING | IMPLEMENTATION | ACCEPTANCE | REVIEW | CLOSE-DOWN | OPERATIONAL SUPPORT | * | Color | PROJECT PHASES | PUBLIC HOLIDAYS
Perform feasibility study | Define Project | Document high-level business requirements | Document current state design | Build IT Infrastructure | Build test packs and scripts | Schedule implementation | Perform final user acceptance | Document post implementation review | Document project closedown report | Manage operational schedule (facilities) | * |  | PREPARATION
Perform risk & impact assessment | Document project definition report | Document high-level technology requirements | Define process model | Build prototype | Perform system testing | Implement IT Infrastructure | Perform final operational acceptance |  | Release resources | Manage availability | * |  | PROJECT DEFINITION
Document business case | Document project plan | Document detailed business requirements | Define organisational chart | Design physical prototype | Perform integration testing | Implement data migration | Signoff implementation completion |  | Perform contract close-out / change-over | Manage capacity | * |  | ANALYSIS
Document umbrella contract | Document quality plan | Document detailed technology requirements | Define location chart | Build physical prototype | Perform user acceptance testing | Perform data extraction routines |  |  |  | Manage performance | * |  | DESIGN
Obtain interim funding | Document resource terms of reference |  | Define data architecture | Test physical prototype | Perform regression testing | Perform data scrubbing & migration routines |  |  |  | Manage backup and recovery | * |  | DEVELOPMENT
| Project definition approved |  | Define application architecture | Implement prototype | Review implementation readiness | Perform data loading routines |  |  |  | Manage disaster recovery | * |  | TESTING
| Agree Contract |  | Define technical architecture | Market and approve prototype |  | Check data validity |  |  |  | Manage against SLAs | * |  | IMPLEMENTATION
| Document vendor/client contract |  | Current state design approved | Prototype authorised |  | Implement application software |  |  |  | Manage security | * |  | ACCEPTANCE
|  |  | Document future state design | Build database |  | Distribute and install application software |  |  |  | Manage data | * |  | REVIEW
|  |  | Define process model | Develop database |  | Test installed application software |  |  |  | Manage on-going training | * |  | CLOSE-DOWN
|  |  | Define organisational chart | Produce database design |  | Implement technology hardware |  |  |  | Support solution (1st/2nd/3rd level) | * |  | OPERATIONAL SUPPORT
|  |  | Define location chart | Build database |  | Distribute and install technology hardware |  |  |  |  | *
|  |  | Define data architecture | Build database testing routines |  | Test installed technology hardware |  |  |  |  | * | E-MAIL TEXTS
|  |  | Define application architecture | Perform database unit testing |  | Implement Business Infrastructure |  |  |  |  | * | Sending Task List to participants:
|  |  | Define technical architecture | Develop data migration |  | Implement processes |  |  |  |  | * | Please find below a list of project tasks for which you have been identified as responsible for. The timing and deliverables for each task reflect those defined in the project plan. Please advise of any issues that you may have regarding this list. Furthermore, regular updates on reporting the progress of these tasks would be greatly appreciated.
|  |  | Future state design approved | Produce data migration design |  | Distribute process & procedural documentation |  |  |  |  | *
|  |  | Perform detailed planning | Build data migration components |  | Check distribution complete |  |  |  |  | *
|  |  | Define organisational change strategy | Build data migration testing routines |  | Implement organisational changes |  |  |  |  | *
|  |  | Define development strategy | Perform data migration unit testing |  | Undertake actual org. changes |  |  |  |  | *
|  |  | Define testing strategy | Database development complete | [6 empty] | *
|  |  | Define implementation strategy | Build application software | [6 empty] | *
|  |  | Define acceptance strategy | Design software configuration | [6 empty] | *
|  |  | Define operational support strategy | Install and configure software components | [6 empty] | *
|  |  |  | Build software testing routines | [6 empty] | *
|  |  |  | Unit test software components | [6 empty] | *
|  |  |  | Software development complete | [6 empty] | *
|  |  |  | Build technology hardware | [6 empty] | *
|  |  |  | Design hardware configuration | [6 empty] | * | Requesting Progress reports:
|  |  |  | Install and configure hardware components | [6 empty] | * | Please find below a list of your outstanding project tasks. In order to monitor the status of the overall project, your co-operation is required to report on the progress of each task. Where possible, please provide the exact number of units completed to date. If the the task has been fully completed, please provide the completion date.
|  |  |  | Build hardware testing routines | [6 empty] | *
|  |  |  | Unit test hardware components | [6 empty] | *
|  |  |  | Hardware development complete | [6 empty] | *
|  |  |  | Build Business Infrastructure | [6 empty] | *
|  |  |  | Build business processes | [6 empty] | *
|  |  |  | Document detailed process model | [6 empty] | *
|  |  |  | Document detailed procedures | [6 empty] | *
|  |  |  | Unit test processes and procedures | [6 empty] | *
|  |  |  | Process development complete | [6 empty] | *
|  |  |  | Undertake communications | [6 empty] | *
|  |  |  | Document communications plan | [6 empty] | *
|  |  |  | Communicate organisational changes | [6 empty] | *
|  |  |  | Communicate system changes | [6 empty] | *
|  |  |  | Measure communications effectiveness | [6 empty] | *
|  |  |  | Communications plan implemented | [6 empty] | *
|  |  |  | Undertake training | [6 empty] | *
|  |  |  | Document training procedures & handbook | [6 empty] | *
|  |  |  | Perform organisational training / re-skilling | [6 empty] | *
|  |  |  | Measure training effectiveness | [6 empty] | *
|  |  |  | Traininng complete | [6 empty] | *
|  |  |  | Build physical locations | [6 empty] | *
|  |  |  | Produce physical location design | [6 empty] | *
|  |  |  | Purchase / build locations | [6 empty] | *
|  |  |  | Unit test locations | [6 empty] | *
|  |  |  | Location development complete | [6 empty] | *
*
*
*
*
*
*
*
*
*
*
*
*
*
*
*
*
*
*
*
*
*
*
*
*
*
*
*
*
*
*
*
*
*
*
*
*
*
*
*
*
*
*
*
*
*